## Product Backlog
Order | Estimation (in hours) | User Stories | Test Cases | Task List | Notes
Must have
Hook to move to an object | 4 | As a User, I want give the player the ability of moving to an object with the hook | has the player been set up? does it effect enemies? are there boxes to use the hook on? | Player class game objects pizza *the hook
hook to activate levers | 1 | as a user, i want to activing levers with the hook | are there levers to hit? | player class Levers Hook
hook to grab objects | 1 | as a user i want to be able to grab objects and pull them to me with the hook | are there boxes to use the hook on? does it pick up the pizza? | Player class Game Objects Hook
Pizza | 0.5 | As a Developer, i want to give the player something that they have to protect throughout the game to give it a more strategic feel | Can we create objects? | player update - respond to keyboard or controller input game world player collision hook collision enemy class *pizza class
Holding Pizza |  | As a Developer, I want to make it more of a challenging game by having the player only be able to hold the pizza and not be able to use their hook or sword. | Is there a pizza? can the player move over the | player update - boolean to check if player has pizza if so actions besides movement can't be made
dropping the pizza (player) | 0.5 | as a user, i want to be able to drop the pizza | can the player drop the pizza? | pizza class player class - *keyboard input
pick up the pizza (player) | 0.5 | as a user i want to be able to pick up the pizza | can the player pick up the pizza? | pizza class player class - *keyboard input
enemy pick up the pizza | 0.5 | as a user i want the enemy to pick up the pizza if left alone | can the enemy pick up the pizza? | pizza class enemy class- update
fight for the pizza | 0.5 | as a user i want to fight for the pizza if a zombie is trying to take it. | can i fight with the enemy if he trys to take the pizza? do i get it back if i win? | pizza class enemy class- update
enemy drop the pizza | 0.5 | as a user i want the enemy to drop the pizza if killed with the pizza | can i kill the enemy with the pizza? if i kill the enemy with the pizza does he drop it? | pizza class enemy class- update
Player Movement | 1 | As a user, i want to move the player with keyboard input | can the game read input from devices. when the keyboard keys on the controller is pressed in a direction does the player move in that direction. when the keyboard keys on the controller is not pressed in a direction does the player stand still | read input from devices. player charater - player update- respond to keyboard/controller input . game world
Zombies | 2 | As a User, I want an enemy that i have to go against to add a new play style | Can we make Enemies? | *Enemy base class - zombie class
movable objects | 1 | as a user i want a box that i can move with my hook | Does the object react when collliding with hook? Does the object move when code is triggered? | hook collision player update movable object update
objects to pull to (immovable) | 1 | as a user i want a box that i can move to with my hook | Do we have a player made? Is the hook set up? has the gameobjects been made? are there pitfalls? | Player class hook class *level design *inmovable objects
health bar | 0.5 | As a user i want to see my health bar | Are we displaying to the screen? does the player have health set up? can the player loose health? can the player gain health | player class - *health *trap class enemy class - *attack
rooms | 8 | As a Level designer I want to breakdown levels into small rooms to simplify the level design | Can you transfer between rooms? Does the camera move to that room? Are the rooms connected? | !game world !room trigger !camera *doors
zombie movement | 2 | As a Developer I want to have movable enemies | Are There Zombies? | Game World Enemy class
zombie chase |  | as a user i want the zombies to chase me down if found | do the zombies have a line of sight? can i get out of his sight once in it? | *zombie - update - move
zombie patrol |  | as a user i want the zombies to patrol around the room | do the zombies move? | *zombie - update - move
zombie fight |  | as a user i want the zombies to fight with me for the pizza | do the zombies know i have the pizza? do i know how the fight is going? | *zombie - update - attack
zombie run away |  | as a user i want the zombie to run away with the pizza | Do the zombies know if they have the pizza? do the zombies know where to go? | *zombie - update - move
door levers | 1 | as a developer i want levers to make puzzles harder | are door triggers connected to the lever? | *lever - update door - !triggers
Should have
timer | 1 | As a User I want to add pressure to the gameplay | can i see the timer? does it go count down? | hud - *update
currency | 1 | As a User I want to have currency to go to the shop | can i see how much i have? can i get more? | player - *update game world game objects
sound indicator | 3 | As a User I want to have sound indicators in the HUD | can i see how much noise im making? | !player class *hud
stealth detector | 1 | As a User I want to have a stealth indicator in the HUD | can i see that im stealthed? | game - *update
fire traps | 1 | as a user i want to be able to be pressured by burning fire | can player get damaged from it? can the trap be avoided? do you collide with the trap? | game world !hook partical effs
electric traps | 1 | as a user i want to be able to have a trap that can shock you | can player get damaged from it? can the trap be avoided? do you collide with the trap? | game world !hook partical effs
spike traps | 1 | as a user i want to be able to fall into traps filled with spikes | can player die from it? can player fall into it? can the trap be avoided? do you collide with the trap? | game world !hook partical effs
enemy spawn trap | 1 | as a user i want to be able to become ambushed by a horde of spawned enemies | can enemies spawn from it? can the trap be avoided? can the trap be triggered? | game world !hook partical effs
music | 1 | As a Player I want to listen to background music while I play | can i change the volume level? | sgd wrappers
sound effects | 3 | As a Player I want to receive feedback for every action I make | can i change the volume level? | sgd wrappers
sword | 2 | As a User I want the ability of fighting enemies | do i start with it? | Player class sword class
smoke bomb | 1 | As a User I want to have a way of escape from an ambush | can i buy more? can i use it every level? can it help solve traps? | Player class Smoke bomb class
Ambush ninja | 2 | As a Developer I want to create an enemy that will only go for the pizza if left alone. | Can we create enemies? can we tell the distance between the player and pizza? does a trigget get sent when the distance is 500? do they drop the pizza if they die with it? can they pick up the pizza? do they have a death timer? do they take damage? do they move? | Enemy class Ambush Ninja class pizza class
Throwing ninja | 2 | As a Developer I want to create an enemy that will sit still and be ranged | Can we create enemies? can they see the player? can they attack? do they alert other enemies? do they take damage? | Enemy class Throwing Ninja class player class
armored zombie | 2 | As a Developer I want to create a stronger version of the standered zombie. | Can we create enemies? do they drop the pizza if they die with it? can they pick up the pizza? do they take damage? do they move? can they target the player? do they fight for the pizza? | Enemy class Zombie class
gluttony/greed | 1 | As a user I want a diffrent boss for the first level | does first hit take the player's money? does the boss move? does the boss attack? does he choose the pizza over the player? can he eat the pizza? | Enemy class Boss1 class
sloth/envy | 1 | As a user I want a diffrent boss for the third level | is the level diffrent? does the move with the play? does the boss change based on how many hits he took? does the boss's postion reset on hit? does the boss attack in the right state? | Enemy class Boss3 class
lust/wrath | 1 | As a user I want a diffrent boss for the second level | does the boss charm? does the boss "get mad"? does the boss take damage from traps? does the boss take damage from sword? are there traps in the room? does the boss move? | Enemy class Boss2 class
pride | 1 | As a user I want a diffrent boss for the final level | does the boss take damage from traps? does the boss taunt you when hit with sword? does the boss move? does the boss attack? | Enemy class Boss4 class
minimap | 1 | as a user i want a way to see the full map | can i use it anywhere? do i start with it? does it show where i have already been? | Level Setup menu states
wayfinding | 1 | as a user i want a way to find out where i need to go | Is it easy to see? does the map help? | level setup ingame message system setup
tug of war with zombie | 1 | As a Developer I want to give the zombies the action of stealing the pizza from player with a minigame | can i see my progress? can i loose? can i win? | player update zombie update
zombie spawn points | 2 | As a Developer I want to have enemies spawn points to create big amount of enemies in each level | does it have zombies to spawn? does it have triggers to spawn them? does it have a limit to spawn? | Enemy class Zombie class spawner class
alarm status | 2 | As a Developer/User I want to have an alarm system call in more enemies when spotted | are there spawn points? do zombies spawn? | Ingame message system setup sound effects loaded in enemy class
pitfalls | 1 | As a Developer I want to have terrain obstacles to increase challenge of gameplay | does the player fall? does the player take damage? does the player animate? | game world physics
trap levers | 1 | As a Developer I want to have trap activation/deactivation elements | are the traps in the same room? are the traps conneted to the levers? are the lever flipping? | lever class traps class
respawn point | 1 | As a Developer I want to have a player spawn point to create new instance of player when he is destroyed | can the player die? can the player fall? are they placed correctly? | player class spawner class level setup
pause menu | 4 | As a User I want to pause the game and have menus | does the game run? does game pause? does a menu show up? can you exit? | menu states
upgrade store | 5 | As a User I want to have a way to improve the character attributes or items | do you have items? do you have attributes? does the shop screen show up? do the attributes change? can you exit? | player class store class
how to play menu | 2 | as a User I want to learn how to play before starting the game | does the screen show up? does it explain all the controls? can you exit? | how to play class main menu class pause menu class
credits menu | 1 | As a Developer I want to give credit to all the people who helped making this game | is everyone listed? can you exit? does it scroll? | credits class main menu class pause menu class
main menu | 1 | As a User I want to have the initial screen before playing the game | can it access the credits menu? can it access the how to play menu? can it start a new game? can it load a old game? can it access the options menu? | Game world menu states
options | 1 | As a User I want to being able of customize the basic game settings | can you change the background volume? can you change the sfx volume? can you change the controler set up? | options class main menu class pause menu class
gamepad input | 1 | As a User I want to being able to play the game with a controller | can you pick up the pizza? can you drop the pizza? can you use your hook? can you use your sword? can you use your smoke bomb? can you move? can you pause the game? | player class main menu credits class how to play options
arcade input | 1.5 | As a User I want to being able to play the game with a arcade controller | can you pick up the pizza? can you drop the pizza? can you use your hook? can you use your sword? can you use your smoke bomb? can you move? can you pause the game? | need player need menus
Could have
currency modifiers | 0.5 | As a Developer I want to reward player's actions | can i gain money? can i see how much money i have? can i see how much money i get? does the player have money? | Player class money data member
enemy AI | 2 | As a Developer I want to create enemy state machine to handle different behavior depending on external input (messages) | Does the enemy change the behavior if he gets NOISE message? Does the enemy change the behavior if he gets PLAYER_SEEN message? Does the enemy behave differently? | enemy level player
Toppings | 1 | As a User I want to have secret items with different rewards | do they spawn? can the ybe picked up? can they be seen? are they explained in the how too? | Game Objects HandleCollision
speed boost | 2 | As a Player I want to have a way to boost my movement speed stats for a short amount of time | do they spawn? can the ybe picked up? can they be seen? are they explained in the how too? can i see it take it effect? does it wear off? does it work? | Entity class game objects enemy class powerup class player class handle collision
attack boost | 2 | As a Player I want to have a way to boost my strength stats for a short amount of time | do they spawn? can the ybe picked up? can they be seen? are they explained in the how too? can i see it take it effect? does it wear off? does it work? | Entity class game objects enemy class powerup class player class handle collision
health up | 2 | As a Player I want to have a way to boost my health | do they spawn? can the ybe picked up? can they be seen? are they explained in the how too? can i see it take it effect? does it wear off? does it work? | Entity class game objects enemy class powerup class player class handle collision
breakable objects | 3 | as a user i want to have a chance to get extra money | do they spawn? can they break? do they drop anything? | game objects handle collision
checkpoints | 4 | As a Developer/Player I want to have a way to keep the play progress | Do we have a player? do we have a level? | Level
particle effects system | 3 | As a Developer I want to give player a feedback with particle system | Do we have a Gameworld? do we have rendering? | Rendering
Ninja outfits | 2 | As an Artist I want to create different playable outfits for player | can I select the outfit? | selection screen
Bonus levels | 8 | As a user I want to achieve secret levels | Do we have a gameworld? do we have levelstates? | Gameworld Level class or state
hard | 4 | as a user i want there to be more then one difficulty | can it be beat? do the ai change? do the drop rates change? | options menu game play enemy class player class
easy | 3 | as a user i want there to be more then one difficulty | can it be beat? do the ai change? do the drop rates change? | options menu game play enemy class player class
meduim | 2 | as a user i want there to be more then one difficulty | can it be beat? do the ai change? do the drop rates change? | options menu game play enemy class player class
secret rooms | 3 | As a Developer I want to have secret rooms in each level to hide the toppings | can you find it? do you get rewarded? can i leave it? | game world game class
shop | 5 | As a User I want to have a shop in the end of each level | can you enter it? can you buy in it? | Player attributes upgrades
Shurikens to buy | 2 | As a User i would like to be able to buy a shuriken to use in the game | Can I buy it? Does my currency decrease the proper amount? Do I get it in the inventory? | Player class Entity class
Kunais to buy |  | As a User I would like to be able to throw a kunai at the enemy | Can i buy items? is there a shop menu? do we have enemies? | Player class Entity class
fight progress bar | 1 | As a User I want feedback when fighting zombies | does it show up? does it change? | player class enemy Class pizza fighting
Longer sword | 1 | As a User I want to be able to get a sword that is longer than the base sword to help fight enemies | Do we have an in game store? can you buy items? | player class store menu sword class
Faster sword | 1 | As a User I want to be able to get a sword that swings faster than the base sword | Do we have an in game store? can you buy items? | player class store menu sword class
Demonic sword | 1 | As a User I want to have an awesome looking demonic sword | Do we have an in game store? can you buy items? | player class store menu sword class
Lifedrain sword | 1 | As a User I want to have a sword that can drain the life of the person it hits | Do we have an in game store? can you buy items? | player class store menu sword class
Player Jump | 3 | As a User I want to give players the ability to jump | does the player react to input? are there shadows? | physics player level
art sketch (unlockeable feature) | 2 | As an Artist I want to share my work with the players | do we have sketches? can they be unlocked? and they uploaded? can it be accessed? can it be viewed? | Main menu
music unlockeables | 3 | As an Artist I want to share my work with the players | do we have other music? can they be unlocked? are they uploaded? can it be accessed? can it be viewed? | Main menu
developer diary unlockeable | 2 | As an developer I want to share my work with the players | can it be unlocked? can it be accessed? can it be viewed? | Main menu
alpha mode | 1 | As an Developer I want to share my early version with the players | can it be unlocked? can it be accessed? can it be played? | main menu alpha release
fake walls (hide) | 2 | As a User I want to have the hide ability in the terrain | are they diffrent from the normal walls? can you hide on them? does it change the bar? are you hidden? | hide mechanics hook player
fake floors (hide) | 3 | As a User I want to have the hide ability in the terrain | are they diffrent from the normal walls? can you hide on them? does it change the bar? are you hidden? | -
Animation Engine | 6 | As a User, I would like to have the character images change depending on what they are doing | are they diffrent from the normal walls? can you hide on them? does it change the bar? are you hidden? | -
doors | 1 | As a Developer I want to be able to create different paths to add requirements to the puzzles | can you tell they are doors? can they be locked? can they be unlocked? can the player pass through them? | -
player attributes | 1 | As a User I want to make a player progress adding upgradable attributes | does the player have movespeed? does the player have health? does the player have strength? is there a shop? can the shop access them? do they change when upgraded? | player
Would be sweet to have
object evasion (pathfinding) | 5 | As a Developer I want to make the enemies more efficient giving the ability of dodge environment objects | Can the enemy move? Does the enemy avoid hitting walls? Does the enemy get stuck between environment objects? | enemy level obstacles (boxes, pitfalls, levers etc
trap evasion (pathfinding) | 3 | As a Developer I want to make the enemies more efficient giving the ability of dodge traps | Can the enemy move? Does the enemy select the shortest path? Does the enemy die by environment hazards? Does the enemy avoid the traps and pitfall holes? | enemy level traps
shortest path (pathfinding) | 9+ | As a Developer I want to make the enemies more efficient using search trees with heuristics | Can the enemy move? Does the enemy select the shortest path? | enemy level previous two pathfinding steps
enemy trap activation | 2 | As a Developer I want to have an enemy skill that activates traps when tghe player is near a trap | Can the enemy move to trap activatior? Can enemy stop in front of the activator? Can enemy activate the trap? Does the enemy keep moving after the trap activation? | trap enemy player level
hook vs wood | 1 | As a User/Artist I want to have a particle effect displaying when the hook collides with wood | Can I see the particle effect? Can I heard the sound effect? does the sound effect stop after the first play? Do the particles die after 2 seconds? | hook player wooden box
hook vs metal | 1 | As a User/Artist I want to have a particle effect displaying when the hook collides with metal | Can I see the particle effect? Can I heard the sound effect? does the sound effect stop after the first play? Do the particles die after 2 seconds? | hook player metallic box
hook vs rock | 1 | As a User/Artist I want to have a particle effect displaying when the hook collides with rock | Can I see the particle effect? Can I heard the sound effect? does the sound effect stop after the first play? Do the particles die after 2 seconds? | hook player rock
invisibility | 1.5 | As a User I want the cheat to be invisible | Can I activate the cheat? Can I deactivate the cheat? Can enemies see me? Can enemies hear me? (should) | Level player enemy
silent | 2 | As a User I want the cheat to be sinlent | Can I activate the cheat? Can I deactivate the cheat? Can enemies see me?(should) Can enemies hear me? (shouldn't) | Level player enemy
light speed | 0.5 | As a User I want the cheat of increase player's speed to the maximum | Can I activate the cheat? Can I deactivate the cheat? Can I move at maximum speed? | Level player enemy
infinite health | 0.5 | As a User I want the cheat to be immortal | Can I activate the cheat? Can I deactivate the cheat? Can I get damage? (shouldn't) Can I die? (shouldn't) | Level player enemy
infinite damage | 0.5 | As a User I want the cheat to deal 9999 damage | Can I activate the cheat? Can I deactivate the cheat? Can I kill any enemy with a single attack? | Level player enemy
survival mode | 6 | As a User I want to have a game mode where my health doesn't regenerate | Does my health regenere? Can I get health when I lvl up? (shouldn't) Can I get more health if I upgrade my attributes?(should) | Player shop level
alternative ending | 3 | As a User I want to see different ending if I get all the toppings | Does the alternative ending display if I get all the toppings? | story mode player
hint system | 3 | As a UserI want to receive in game help | Can I turn on the hints? Can I turn off the hints? Does the game display the hints? Do the hints display properly? (without blocking the user's vision) | Level Camera player
achievements | 3 | As a User I want to be able of checking all the achievements that I have unlocked | Can I acces tehe achievement menu? Do I see the progress in each achievement? Does the game display a message when I unlock an achievement? | main menu achievements
no alarm (achievement) | 1 | As a User I want to earn an achievement if i don't alert any enemy in the level | Can I earn the achievement if I complete a level without alatrming the enemies? | player level enemies alarm levels
all toppings (achievement) | 2.5 | As a User I want earn an achievement if I find all the toppings in all levels | Can I earn the achievements if I have all the toppings? | player story mode bosses enemies
beat the game (achievement) | 1 | As a User I want to earn an achievement when I beat the game | Can I earn the achievement if I beat the game? | player story mode bosses enemies
sword mastery (sword skill) | 1 | As a User I want I want a passive skill that increases the player's sword mastery (+2% damage. +2% speed) | Does the skill improve player's damage? Does the skill improve the player's skill? Do I still keep the passive if I die? | Player level swiord
Requiem (sword skill) | 3 | As a User I want a sword skill that hurts the player (-20hp) but gives +75% damage in the next 15s | Can I die if I use this skill? (shouldn't die -> can't use) Can I cast the skill? Do I make more damage? Do I have a timer to indicate the remaining skill time? Does it display a visual effect when I use the skill? | Player level sword
LA Slash (sword skill) | 3 | As a User I want the skill of a larger slash that creates an air wave (ranged attack) | Does the skill perform when I press proper command? (key press) Does the skill play the animation? Does the slash dissapear when it hits an obstacle? Does the slash damage the enemies? | player Level enemies
enter name (high score) | 1 | As a User I want to be able of entering my name in my score | Do I see if I beat the existing high score? (10 entries)
save high score | 1 | As a User I want to save high score if I beat existing one | Can I save the score? does it create a file if it doesn't exit? | Level player
load high scores | 1 | As a User I want to load high scores | Can I load the high scores? Does it order the entries sort by score descending ? | Main menu
high score menu | 2 | As a User I want to access to high scores | Can I access the high score menu? Can I see all the entries clearly? Can I exit? Does it go back to main menu? | Main menu load high score
hardcore mode | 1 | As a layer I want to have the hardcore game mode. If I set the alarm I get Game over. | Can I set the alarm? Do I lose if I set the alarm? can I complete the level? Does the sound detector work? | main story mode Level Player Enemy
replacement skill | 2 | As a User I want to havethe skill of dodging the first attack putting a wooden replacement | Can I dodge the first attack if I have the skill active? Does the player appear inm the new location without glitching in the environment? Does the enemy change the target from the wood? | enemy player level
shadow skill | 3 | As a user I want to have a skill of controlling environment shadows | Can I control the shadows? Can I see what shadow am I controlling? Can I hide when I use controlled shadows? | Shadows player enemy alert levels level
selfcopy skill | 3 | As a User I want to have tje skill of creating an image of the player to distract the guards | Can the fcopy move? Does the copy alert the guards? (shouldn't just make noise) does the copy dissapear after 8s? | Player level Enemy
boss ultimate ability | 3 | As a User I want to see the bosses with skill to make massive damage to player | Can the boss move? can the boss prform the ability? does the ability damage the player? | level boss player
execution kill (dynamics) | 3 | As a User I want only perform the execution if the enemies aren't in alert state and if the player is behind the target (kill with a single sword swing) | Can I perform the skill? Does the skill kill the enemy? | Player enemy level
silent kill (noise) | 2 | As a User I don't want to make any noise (alert the other enemies) when I kill an enemie | Does the kill make sound? | Player enemy level
silent kill animation | 2 | As a User I want to see an animation when I perform the silent kill | Does the animation play when I make the silent kill move? | enemy Player silent kill skill sound detector
trap deactivation minigame | 8 | As a User I want to have a way to deactivate traps | Can i select the trap? Can I enter the minigame? Does the rest of the level (enemies, traps etc) freeze? (should) Can I exit the minigame? Does the trap damage me if I fail? | Trap minigame trap level player
usable item inventory | 1 | As a UserI want to make visible what items are in the inventory | Can I see the inventory? Can I see what item is selected? can I use selected item? when the number is 0 does the item disappear or display a 0? | usable items player level
Puzzles that work with items | 3 | As a User I want to have puzzles that require to search certain objects to complete the puzzle | Can I create new puzzle? | puzzle level player
puzzle items | unknown | As a User I want to have items in the level to solve puzzles | Can I create new items? Does it solve the puzzle? Can I use the item for combat? (shouldn't) | item puzzle
create secondary quests | 3 | As a Developer I want to create secondary quest system | Can I create new secondary quests? | "player level Secondary quests
set the money earned on secondary quest | 1 | As a Developer I want to set the reward of the secondary quests | Can I customize the secondary quests? Can I set the reward? | player level Secondary quests
check progress secondary quest | 2 | As a User I want to have an indicator of the progress of the secondary quests | Can I progress in secondary quests? Can I see the progress? | player level Secondary quests
cut-scenes | 6 | As an Artist I want to make the game story appeal to player | Can I watch the cut-scenes? Does it have sound? does it have coherence? | cut-scenes
additional playable characters | 4 | As a Player I want to create more playable characters | Can I select different characters? Does the characters display clearly? Do I know exactly which character is selected? | character select screen different characters
additional playable characters (attributes) | 3 | As a Player I want to have different attribbutes for different characters | Can I see the attribute difference? Do the attributes have impact in the game? (example: more/less damage) | different character scripts Character assets
brightness control | 1 | As a Player I want to have control on the game brightness | Can I change the brightness? Does it display the change in numbers? | option menu
parental control mode (without blood) | 1 | As a Parent/Developer I want to choose the gore mode (on - off0 to protect the children | Can I change the blood mode? | option menu
Player ranged weapons | 3 | As a Player I want to have the possibility to attack from afar | Can I shoot the weapon? Does it display the shooting animation? Does it display the sound? | Player Level
Player ranged weapons counter | 0.5 | As a player I want to have the count of the remaining bullets | Can I see the projectile amount? Does it decrease/increase? | ranged weapon Level player
Player ranged weapons distance | 1 | As a player I want the ranged weapon distance. A clear display of the range | Does the range display? Can I change the distance? Can I move the diagram? | Player ranged weapon level
enemy spawn points | 2 | As a Developer I want to have spawn points to populate levels | Can I set enemy type? Can I custom the parameters? Does the enemy spawn? | enemies level
Summon helping NPC (minion) | 4 | As a User I want to have a special skill that summons a minion controlled by the CPU to help me | Can I cast the summon? Does the minion appear when I summon it? | player minion asset summoning skill behavior script
Move helping NPC (minion) | 1 | As a User I want the minion has motion | Can the minion move? can the minion patrol? | minion movement script minion asset
Attacking helping NPC (minion) | 1 | As a user I want to have the minion has attacks | Can the minion attack? Can the minion die? Can minion target the enemy that is attacking the player? | enemy player minion asset
Interactive helping NPC (minion) | 2 | As a user I want to have the minion has skills to interact with the environment (activate levers) | Can minion activate levers? Can minion follow the player? | minion asset minion script (AI) player
zombie mode | 9 | As a User I want to play as a zombie master | Can I control the zombie? Can the CPU move the player? Can Cpu attack enemies? Can CPU win the game? can CPU evaluate the main goal ? (deliver the pizza) Can I attack the CPU? Can CPU drop the pizza? Can CPU use skills? | zombie input CPU controlled player game logic CPU respawn pizza behavior world
vs mode (fastest delivery) | 4 | As a User I want to play multiplayer version of the game | Can I play with two controllers? Can each controller move only one of the players? Can I hurt the other player? Can I win the game? Can enemies target only one player at a time? Can one player win? Can one player lose? Can I steal the pizza having my own pizza equiped? (shouldn't) | two input script two player assets game logic score system enemies two pizzas
ultimate attack | 2 | As a UserI want to have a massive damage attack (player) | Can I cast the attack? Does the attack play the animation? does it collide? does it affect the enemies? | sword Player animation attack behavior script
ultimate attack cooldown | 0.5 | As a User I want a cooldown to not being able of spamming the ultimate attack | Can I spam the skill? (I shouldn't) | sword Player ultimate attack
infinite tower mode (kill enemies) | 3 | As a Developer I want to create the infinite game mode. In this mode the goal is killing all the enemies | Can I kill enemies? Can I get score? Can I complete a level? Can I go to the next level? Can I upgrade my attributes? | single level complete enemy spawn points shop score counter timer
shuriken and kunai minigame | 4 | As a Developer I want to create a way to learn how to use ranged weapons | Can I aim? Can I shoot? Does the proyectile get affected by physics? Does proyectile accelerate (desaccelerate)? does the proyectile collide? Does the proyectile make damage? | kunai asset shuriken asset proyectile behavior physic engyne gravity normal force calculation
wooden floor | 1 | As an Artist I want to create a wooden floor tile | Can I see the tile? Can the player walk on this tile? can the enemies walk on this tile? Does player make any noise in this floor? | player one enemy tile drawer noise detector noise engine
metallic floor | 1 | As an Artist I want to create a metallic floor tile | Can I see the tile? Can the player walk on this tile? can the enemies walk on this tile? Does player make any noise in this floor? | player one enemy tile drawer noise detector noise engine
rock floor | 1 | As an Artist I want to create a rock floor tile | Can I see the tile? Can the player walk on this tile? can the enemies walk on this tile? Does player make any noise in this floor? | player one enemy tile drawer noise detector noise engine
tatami floor | 1 | As an Artist I want to create a tatami floor tile | Can I see the tile? Can the player walk on this tile? can the enemies walk on this tile? Does player make any noise in this floor? | player one enemy tile drawer noise detector noise engine
load game with xml | 2 | As a Developer I want to manage the file load with xml | Does it load (something)? Does it load proper game status? does it play the loading screen? does it start a loaded the game? | xml manager save game manager level loader
save game in xml | 2 | As a Developer I want to manage the file save with xml | Does it create the file? Does it save the file? Does it save properly the game status? | xml manager asset namings
load game assets with xml | 5 | As a Developer I want to manage the game elements with xml | Can I read the xml file? Does it load? Does it load properly the assets? does it load all the assets? | xml manager xml parser all assets
Level creator (size) | unknown | As a Developer/User I want to have tool to create an empty level | Can I create the level? Can I resize the level? Can I place rooms into the level? Can I place the camera initial position | level creator (core) camera.behavior
Level creator (tiles) | unknown | As a Developer/User I want to have tool to place terrain tiles | Can I place tiles? Can I move tiles? Can I delete tiles? Can I give physics to the ties? Can I set tile behavior? | tile assets tile behavior script tile physics
Level creator (enemies) | unknown | As a Developer/User I want to have tool to place enemies | Can I select enemies from the pallete? Can I place enemies in the level? Can I hide/show enemies? Can I delete enemies? Can I edit the enemy attributes? Can I select placed enemies? | enemy editor enemy script enemy assets trigger creator
Level creator (spawn points) | unknown | As a Developer/User I want to have tool to place spawn points | Can I set the spawn point? Can I select the enemy type? Can I edit the spawn timer? Can I edit the spawn trigger? is it shown in the game? | enemy units player spawn point (class)
Level creator (objects) | unknown | As a Developer/User I want to have tool to place different objects (boxes, levers etc) | Can I select objects from the pallete? Can I place objects? Can I move objects? Can I select placed objects? Can I delete objects? | all the objects (tiles, boxes, terrains, doors, etc) collision manager enemies AI scripts player toppings traps trap scripts
Level creator (save) | unknown | As a Developer/User I want to have tool to save created level | Can I save the created level? Does it creates a proper extension file? Does it have proper content ? | level (asset) parser xml creator
Level creator (play) | unknown | As a Developer/User I want to have tool to play saved level | Can I select the level? Does the level load all the elements properly? Can I play the level? | Level selction menu (previous elements like player, assets etc...)
Won't have